## POA&M Metrics
ADMINISTERING ENTITY: | 0
SYSTEM NAME:
SYSTEM ACRONYM:
CURRENT FISCAL YEAR: | 0
Plan of Action and Milestone (POA&M) Metrics Totals (Security, Other & Privacy Combined) |  | Number of POA&M Items By Security Control Family | TOTAL Open | Ongoing | Delayed | Completed | Number of POA&M Items By Privacy Control Family | Total Open | Ongoing | Delayed | Completed
POA&M Findings by Weakness Status |  | AC | 0 | 0 | 0 | 0 | AP | 0 | 0 | 0 | 0
ONGOING | 0 | AT | 0 | 0 | 0 | 0 | AR | 0 | 0 | 0 | 0
DELAYED | 0 | AU | 0 | 0 | 0 | 0 | DI | 0 | 0 | 0 | 0
COMPLETED | 0 | CA | 0 | 0 | 0 | 0 | DM | 0 | 0 | 0 | 0
Total | 0 | CM | 0 | 0 | 0 | 0 | IP | 0 | 0 | 0 | 0
|  | CP | 0 | 0 | 0 | 0 | SE | 0 | 0 | 0 | 0
Open Findings by Risk Level |  | IA | 0 | 0 | 0 | 0 | TR | 0 | 0 | 0 | 0
HIGH | 0 | IR | 0 | 0 | 0 | 0 | UL | 0 | 0 | 0 | 0
MODERATE | 0 | MA | 0 | 0 | 0 | 0
LOW | 0 | MP | 0 | 0 | 0 | 0
Total | 0 | PE | 0 | 0 | 0 | 0
|  | PL | 0 | 0 | 0 | 0
Total# of Open Findings (Ongoing & Delayed) | 0 | PS | 0 | 0 | 0 | 0
|  | RA | 0 | 0 | 0 | 0
|  | SA | 0 | 0 | 0 | 0
|  | SC | 0 | 0 | 0 | 0
|  | SI | 0 | 0 | 0 | 0
|  | PM | 0 | 0 | 0 | 0
|  | Other | 0 | 0 | 0 | 0
Plan of Action and Milestone (POA&M) Metrics Totals (Security Only) |  | MARS-E 2.0 Gap Analysis Tracking | TOTAL Open | Ongoing | Delayed | Completed
POA&M Findings by Weakness Status |  | MARS-E V. 1.0 | 0 | 0 | 0 | 0
ONGOING | 0 | MARS-E V. 2.0 | 0 | 0 | 0 | 0
DELAYED | 0
COMPLETED | 0
Total | 0
Open Findings by Risk Level
HIGH | 0
MODERATE | 0
LOW | 0
Total | 0
Total# of Open Findings (Ongoing & Delayed) | 0
Plan of Action and Milestone (POA&M) Metrics Totals (Privacy Only)
POA&M Findings by Weakness Status
ONGOING | 0
DELAYED | 0
COMPLETED | 0
Total | 0
Open Findings by Risk Level
HIGH | 0
MODERATE | 0
LOW | 0
Total | 0
Total# of Open Findings (Ongoing & Delayed) | 0
Plan of Action and Milestone (POA&M) Metrics Totals (Other Only)
POA&M Findings by Weakness Status
ONGOING | 0
DELAYED | 0
COMPLETED | 0
Total | 0
Open Findings by Risk Level
HIGH | 0
MODERATE | 0
LOW | 0
Total | 0
Total# of Open Findings (Ongoing & Delayed) | 0

## POA&M Template
ADMINISTERING ENTITY:
SYSTEM NAME:
SYSTEM ACRONYM:
CURRENT FISCAL YEAR:
System Name |  | System Acronym | System Critically as defined by FIPS | Confidentiality |  | Availability | Integrity | If no weaknesses identified, provide a reason
|  |  | Moderate | Moderate |  | Moderate | Moderate
Weakness Identifier | Control Family | Control Details | Weakness Description | Weakness Source | POC | Resources Required | Scheduled Completion Date | Milestones With Completion Dates | Changes to Milestones Date | Completion Date | WeaknessStatus | Risk Level | MARS-E Version | Compensating Controls | Comments

## POA&M Instructions
ADMINISTERING ENTITY:
SYSTEM NAME:
SYSTEM ACRONYM:
CURRENT FISCAL YEAR:
System Name |  | System Acronym | System Critically as defined by FIPS | Confidentiality |  | Availability | Integrity | If no weaknesses identified, provide a reason
0 |  |  | Moderate | Moderate |  | Moderate | Moderate
Weakness Identifier | Control Family | Control Details | Weakness Description | Weakness Source | POC | Resources Required | Scheduled Completion Date | Milestones With Completion Dates | Changes to Milestones Date | Completion Date | WeaknessStatus | Risk Level | MARS-E Version | Compensating Controls | Comments
1
2
3
4
5
6
8
9
11
10
12
13
7
14
15
16
18
17
19
20
21
1. Administering Entity: Please enter the state, territory or name of the administering entity.
2. System Name: Please enter the system name.
3. System Acronym: Please enter the system acroynm.
4. Current Fiscal Year: Please enter the current fiscal year.
5. System Name [No Action Required]: This field is auto-filled from the name entered in instruction# 2.
6. System Acronym [No Action Required]: This field is auto-filled from the acronym entered in instruction# 3.
7. System Criticality: This will be moderate for any system connecting to the Federal Data Services Hub.
8. Confidentiality: This will be moderate for any system connecting to the Federal Data Services Hub.
9. Availablity: This will be moderate for any system connecting to the Federal Data Services Hub.
10. Integrity: This will be moderate for any system connecting to the Federal Data Services Hub.
11. If no weaknesses identified, provide a reason [Drop- down list provided]:
Choose from the following six options: - All weaknesses eliminated - No review conducted - No weaknesses found - System in development - System reclassified – not a system - System retired
12. Weakness Identifier: A unique number assigned to each POA&M entry that is used to track the weakness. Typically the weakness identifier is comprised of the following: System name/acronym; Quarter (A, B C, or D) and Fiscal Year the weakness was first recorded; and a sequence number. (example: SYSTEM_A_2014_3).
13. Control Family [Drop-down list provided]: Please chose the control family or category that best signifies the origin of the finding.
Choose from the following Options:
- Other
- - AC
- AT
- AU
- CA
- CM
- CP
- IA
- IR
- MA
- MP
- PE
- PL
- PS
- RA
- SA
- SC
- SI
- PM
-Privacy-AP
-Privacy-AR
-Privacy-DI
-Privacy-DM
-Privacy-IP
-Privacy-SE
-Privacy-TR
-Privacy-UL
14. Control Details: Enter the security control(s) in which the weakness was discovered (examples: AC-2, AU-10, IR-2, and SA-9). Multiple controls may be entered if applicable.
15. Weakness Description: Description of the vulnerability or risk identified. This information may be found in the Security Assessment Report (SAR) or other security audit type report.
16. Weakness Source: A source shall be reported for all weaknesses. When recording the weakness source, both the type of review and the date on which the review was conducted or published shall be provided. If the weakness represents a repeat finding, each source in which the weakness was identified shall be documented.
17. Point of Contact (POC): A POC shall be identified and documented for each weakness. The POC shall at a minimum refer to the position/role responsible for resolving the weakness(examples: Information System Security Officer [ISSO], Privacy Coordinator, System Owner), a contact telephone number, and/or an email address.
18. Resources Required: The resources required to successfully complete the weakness shall be estimated and documented. The estimate shall be based on the total resources required to fulfill all the milestones necessary for weakness mitigation. Resources shall be estimated as monetary value and/or staffing requirements. When identifying monetary value, the amount shall be categorized as New Funding, Existing Funding, or Reallocated Funding. Staffing requirements shall be estimated as staff-hours or full time equivalents (FTEs) and categorized as New Staff or Existing Staff.
19. Scheduled Completion Date: A completion date shall be assigned to every weakness, to include the month, day, and year using the format: MMDDYYYY. This date is the estimated date in which all milestones for the weakness will be completed and the weakness closed. The scheduled completion date shall not change once recorded.
20. Milestones with Completion Dates: Each weakness shall have at least one milestone with an associated completion date to facilitate corrective action. A milestone will identify specific requirements or key steps to correct an identified finding/action item. Milestone(s) with completion date entries, once recorded, shall not be removed or changed. Even if you only have ONE milestone it still needs to contain a completion date.
For ease of reading and managing, it is recommended you number your milestones as shown in the sample below and on the POA&M Sample Tab. All milestones should be entered in the single cell provided that cooresponds with the identified weakness.
(1) Milestone1 08/10/2014
(2) Milestone2 09/15/2014
(3) Milestone3 10/30/2014
21. Changes to Milestone Completion Dates: Any necessary revision to the original milestone completion date(s) due to the original date being surpassed because additional time or resources are required, shall be documented. This revised Milestone Completion Date(s) does not replace the original Milestone Completion Date, but is an amendment.
For ease of reading and managing, it is recommended you number your milestone changes as shown in the sample below and on the POA&M Sample Tab. It is also recommended you start with the milestone in which the plan has changed. All milestones should be entered in the single cell provided that cooresponds with the identified weakness.
(2) Milestone2 10/01/2014
(3) Milestone3 11/15/2014
22. Completion Date: The date that all of the weakness milestones have been completed and the weakness can be closed.
23. Weakness Status [Drop-down list provided]: A status shall be assigned to each weakness.
Chose from the following three options:
Completed—This status is assigned when all corrective actions have been completed for a weakness such that the weakness is successfully mitigated. Documentation shall be required to demonstrate the weakness has successfully been resolved. The Date of Completion shall be recorded for a completed weakness. Ongoing—This status is assigned only when a weakness is in the process of being mitigated and has not yet exceeded the associated Scheduled Completion Date. Delayed—This status is assigned when a weakness is being mitigated after the associated Scheduled Completion Date has passed. An explanation shall be provided in the Weakness Comments field.
24. Risk Level [Drop-down list provided]: Risk level of weakness identified in SAR, Audit or Review. The assignment of risk levels should follow the methodology outlined in NIST 800-30 Appendices G,H, and I. In assigning risk levels, CMS requires only 3 levels of granularity: High, Moderate, and Low. (See the Risk Calculation Instructions tab for additional information).
The 3 risk levels can be defined as the following:
High: High risk means that a threat event could be expected to have a severe or catastrophic adverse effect on organizational operations, organizational assets, individuals, other organizations, or the Nation.
Moderate: Moderate risk means that a threat event could be expected to have a serious adverse effect on organizational operations, organizational assets, individuals,other organizations, or the Nation
Low: Low risk means that a threat event could be expected to have a limited adverse effect on organizational operations, organizational assets, individuals,other organizations, or the Nation
Choose from the following three options:
High
Moderate
Low
25. MARS-E Version: This field is provided to identify the weaknesses associated with the MARS-E Version 2.0 Gap Analysis.
Choose from the following two options:
MARS-E V. 1.0
MARS-E V. 2.0
26. Compensating Controls: Please list and describe any compensating controls that have been put in place in lieu of the prescribed control(s).
27. Comments: Any additional information or details necessary to clarify weakness information, status and/or traceability shall be documented in the Weakness Comments field.
22
23
24
25
26
27

## Risk Calculation Instructions
From Appendix G
Likelihood of Occurrence
Table G-2: Assessment Scale - Likelihood of Threat Event Initiation (Adversarial)
Qualitative Values | Semi-Quantitative Values |  | Description
Very High | 96-100 | 10 | Adversary is almost certain to initiate the threat event.
High | 80-95 | 8 | Adversary is highly likely to initiate the threat event.
Moderate | 21-79 | 5 | Adversary is somewhat likey to initiate the treat event.
Low | 5-20 | 2 | Adversary is unlikely to initiate the threat event.
Very Low | 0-4 | 0 | Adversary is highly unlikely to initiate the threat event.
Table G-3: Assessment Scale - Likelihood of Threat Event Occurance (Non-Adversarial)
Qualitative Values | Semi-Quantitative Values |  | Description
Very High | 96-100 | 10 | Error, accident, or act of nature is almost certain to occur; or occurs more than 100 times a year.
High | 80-95 | 8 | Error, accident, or act of nature is highly likely to occur; or occurs between 10-100 times a year.
Moderate | 21-79 | 5 | Error, accident, or act of nature is somewhat likely to occur; or occurs between 1-10 times a year.
Low | 5-20 | 2 | Error, accident, or act of nature is unlikely to occur; or occurs less than once a year, but more than once every 10 years.
Very Low | 0-4 | 0 | Error, accident, or act of nature is highly unlikely to occur; or occurs less than once every 10 years.
Table G-4: Assessment Scale - Likelihood of Threat Event Resulting in Adverse Impacts
Qualitative Values | Semi-Quantitative Values |  | Description
Very High | 96-100 | 10 | If the threat event is initiated or occurs, it is almost certain to have adverse impacts.
High | 80-95 | 8 | If the threat event is initiated or occurs, it is highly likely to have adverse impacts.
Moderate | 21-79 | 5 | If the threat event is initiated or occurs, it is somewhat likely to have adverse impacts.
Low | 5-20 | 2 | If the threat event is initiated or occurs, it is unlikely to have adverse impacts.
Very Low | 0-4 | 0 | If the threat event is initiated or occurs, it is highly unlikely to have adverse impacts.
Table G-5: Assessment Scale - Overall Likelihood
Likelihood of Threat Event Initiation or Occurrence | Likelihood Threat Events Result in Adverse Impacts
| Very Low | Low | Moderate | High | Very High
Very High | Low | Moderate | High | Very High | Very High
High | Low | Moderate | Moderate | High | Very High
Moderate | Low | Low | Moderate | Moderate | High
Low | Very Low | Low | Low | Moderate | Moderate
Very Low | Very Low | Very Low | Low | Low | Low
From Appendix H
Impact
Table H-2: Examples of Adverse Impacts
Type of Impact |  | Impact
Harm to Operations |  | (1) Inability to perform current missions/business functions. -In a sufficiently timely manner. -With sufficient confidence and/or correctness. -Within planned resource constraints (2) Inability, or limited ability, to perform missions/business functions in the future. -Inability to restore missions/business functions. -In a sufficiently timely manner. -With sufficient confidence and/or correctness. -Within planned resource constraints. (3) Harms (e.g., financial costs, sanctions) due to noncompliance. -With applicable laws or regulations. -With contractual requirements or other requirements in other binding agreements (e.g., liability). (4) Direct financial costs. (5) Relational harms. -Damage to trust relationships. -Damage to image or reputation (and hence future or potential trust relationships).
Harm to Assets |  | (1) Damage to or loss of physical facilities. (2) Damage to or loss of information systems or networks. (3) Damage to or loss of information technology or equipment. (4) Damage to or loss of component parts or supplies. (5) Damage to or of loss of information assets. (6) Loss of intellectual property.
Harm to Individuals |  | (1) Injury or loss of life. (2) Physical or psychological mistreatment. (3) Identity theft. (4) Loss of Personally Identifiable Information. (5) Damage to image or reputation.
Harm to Other Organizations |  | (1) Harms (e.g., financial costs, sanctions) due to noncompliance. -With applicable laws or regulations. -With contractual requirements or other requirements in other binding agreements. (2) Direct financial costs. (3) Relational harms -Damage to trust relationships. -Damage to reputation (and hence future or potential trust relationships).
Harm to Nation |  | (1) Damage to or incapacitation of a critical infrastructure sector. (2) Loss of government continuity of operations. (3) Relational harms. -Damage to trust relationships with other governments or with nongovernmental entities. -Damage to national reputation (and hence future or potential trust relationships). (4) Damage to current or future ability to achieve national objectives. -Harm to national security.
Table H-3: Assessment Scale - Impact of Threat Events
Qualitative Values | Semi-Quantitative Values |  | Description
Very High | 96-100 | 10 | The threat event could be expected to have multiple severe or catastrophic adverse effects on organizational operations, organizational assets, individuals, other organizations, or the Nation.
High | 80-95 | 8 | The threat event could be expected to have a severe or catastrophic adverse effect on organizational operations, organizational assets, individuals, other organizations, or the Nation. A severe or catastrophic adverse effect means that, for example, the threat event might: (i) cause a severe degradation in or loss of mission capability to an extent and duration that the organization is not able to perform one or more of its primary functions; (ii) result in major damage to organizational assets; (iii) result in major financial loss; or (iv) result in severe or catastrophic harm to individuals involving loss of life or serious life-threatening injuries.
Moderate | 21-79 | 5 | The threat event could be expected to have a serious adverse effect on organizational operations, organizational assets, individuals other organizations, or the Nation. A serious adverse effect means that, for example, the threat event might: (i) cause a significant degradation in mission capability to an extent and duration that the organization is able to perform its primary functions, but the effectiveness of the functions is significantly reduced; (ii) result in significant damage to organizational assets; (iii) result in significant financial loss; or (iv) result in significant harm to individuals that does not involve loss of life or serious life-threatening injuries.
Low | 5-20 | 2 | The threat event could be expected to have a limited adverse effect on organizational operations, organizational assets, individuals other organizations, or the Nation. A limited adverse effect means that, for example, the threat event might: (i) cause a degradation in mission capability to an extent and duration that the organization is able to perform its primary functions, but the effectiveness of the functions is noticeably reduced; (ii) result in minor damage to organizational assets; (iii) result in minor financial loss; or (iv) result in minor harm to individuals.
Very Low | 0-4 | 0 | The threat event could be expected to have a negligible adverse effect on organizational operations, organizational assets, individuals other organizations, or the Nation.
From Appendix I
Risk Determination
Table I-2: Assessment Scale - Level of Risk (Combination of Likelihood and Impact)
Likelihood (Threat Event Occurs and Results in Adverse Impact) | Level of Impact
| Very Low | Low | Moderate | High | Very High
Very High | Very Low | Low | Moderate | High | Very High
High | Very Low | Low | Moderate | High | Very High
Moderate | Very Low | Low | Moderate | Moderate | High
Low | Very Low | Low | Low | Low | Moderate
Very Low | Very Low | Very Low | Very Low | Low | Low
Table I-3: Assessment Scale - Level of Risk
Qualitative Values | Semi-Quantitative Values |  | Description
Very High | 96-100 | 10 | Very high risk means that a threat event could be expected to have multiple severe or catastrophic adverse effects on organizational operations, organizational assets, individuals, other organizations, or the Nation.
High | 80-95 | 8 | High risk means that a threat event could be expected to have a severe or catastrophic adverse effect on organizational operations, organizational assets, individuals, other organizations, or the Nation.
Moderate | 21-79 | 5 | Moderate risk means that a threat event could be expected to have a serious adverse effect on organizational operations, organizational assets, individuals, other organizations, or the Nation.
Low | 5-20 | 2 | Low risk means that a threat event could be expected to have a limited adverse effect on organizational operations, organizational assets, individuals, other organizations, or the Nation.
Very Low | 0-4 | 0 | Very low risk means that a threat event could be expected to have a negligible adverse effect on organizational operations, organizational assets, individuals, other organizations, or the Nation.
In determining risk levels, please become familiar with NIST Special Publication 800-30 Revision 1.
Below are tables from NIST Special Publication 800-30 Revision 1 for your reference. In assigning risk levels, CMS requires only 3 levels of granularity: High, Moderate, and Low. When utilzing the NIST tables from NIST 800-30 Revision 1, Appendices G,H, and I, please consolidate Very High with High and Very Low with Low.

## POA&M Sample
STATE-BASED ADMINISTERING ENTITY: |  |  | Virginia
SYSTEM NAME: |  |  | VA Test System
SYSTEM ACRONYM: |  |  | VATESTSYS
CURRENT FISCAL YEAR: |  |  | 2014
System Name |  | System Acronym | System Critically as defined by FIPS | Confidentiality |  | Availability | Integrity | If no weaknesses identified, provide a reason
VA Test System |  | VATESTSYS | Moderate | Moderate |  | Moderate | Moderate
Weakness Identifier | Control Family | Control Details | Weakness Description | Weakness Source | POC | Resources Required | Scheduled Completion Date | Milestones With Completion Dates | Changes to Milestones Date | Completion Date | WeaknessStatus | Risk Level | Compensating Controls | Comments
TESTSYS_A_2014_2 | AC | AC-2 | Account Management process is not documented. | Initial Security Assessment Review 02/12/13 | John Doe, CISO | 8 hours Existing Staff | 2013-03-15 | (1) Create an account management process 2/28/2013 (2) Document process 03/01/2013 (3) Review process with staff 03/10/2013 (4) Implement Process 03/12/2013 (5) Review effective of new process 03/14/2013 (6) Update POA&M 03/15/2013 | (1) Create an account management process 2/15/2013 (2) Document process 02/20/2013 (3) Review process with staff 02/25/2013 (4) Implement Process 02/26/2013 (5) Review effective of new process 02/28/2013 (6) Update POA&M 03/01/2013 | 2013-03-01 | Completed | Moderate | N/A
TESTSYS_A_2013_1 | PE | PE-10 | There is no EPO in server room 1. | Initial Security Assessment Review 02/12/13 | John Doe, CISO | 20 hours Existing Staff $65,000 Professional Services and Equipment | 2013-08-01 | (1) Solicit vendors to provide EPO solution and estimate of cost 02/25/2013 (2) Choose vendor to perform work 04/15/2013 (3) Initiate the install of the emergency power shutoff solution 07/01/2013 (4) Test the implemented EPO solution 07/15/2013 (5) Finalize solution and update POA&M 08/01/2013 | (3) Initiate the install of the emergency power shutoff solution NEW DATE 05/01/2014 (4) Test the implemented EPO solution 05/15/2014 (5) Finalize solution and update POA&M 06/01/2014 |  | Delayed | Moderate | N/A | Awaiting funding to implement EPO solution
TESTSYS_A_2013_1 | IA | IA-5 | Update the control implementation statement to document the processes used to implement control requirements a-f, h, and i. | SSP Review 06/10/2013 | John Doe, CISO | 10 hours Existing Staff | 2013-07-30 | (1) Update the implementation standards a-f, h, and I for IA-5 in the SSP 06/20/2013 (2) Review changes to the SSP with the security staff 07/01/2013 (3) Finalize the implementation standards based on staff comments and recommendations 07/30/2013 |  | 2013-07-30 | Completed | Low | N/A
TESTSYS_A_2014_3 | PE | PE6.2 | Lack of processes for: (a) reviewing physical access logs at least once every two months, and (b) coordinating results of reviews and investigations with the organization's incident response capability. | Annual Attestation 03/01/2014 | John Doe, CISO | 20 hours Existing Staff | 2014-05-20 | (1) Create a process reviewing physical access logs at least once every two months and coordinating results of reviews and investigations with the organization's incident response capability:: 3/8/2014 (2) Document process 04/01/2014 (3) Review process with staff 04/15/2014 (4) Implement Process 05/01/2014 (5) Review effective of new process 05/15/2014 (6) Update POA&M 05/20/2014 |  |  | Ongoing | Low | N/A
TESTSYS_A_2014_4 | SI | SI-2 | Windows server BD1-3 has not been patched in 3 months | Annual Attestation 03/01/2014 | John Doe, CISO | 40 hours Existing Staff | 2014-03-15 | (1) Develop a plan and schedule to patch the servers monthly. Update the SSP to reflect the plan to patch the servers 03/15/2014 (2) Test the outstanding patches in the test environment (3) Implement patches on the production server | (2) continuing testing in the test environment (3) Implement patches on the production server |  | Delayed | High | N/A | Need additional testing due to possible adverse affects of applying the patch. MS14-013 (KB2929961)
TESTSYS_A_2014_5 | RA | RA-5 | The organization does not employ vulnerability scanning tools | Annual Attestation 03/01/2014 | John Doe, CISO | 80 hours Existing Staff $3000 Tools and Training | 2014-04-01 | (1) Shop vulnerability scanning tools 03/05/2014 (2) Select vulnerability scanning tool 03/10/2014 (3) Obtain training on the product 03/15/2014 (4) Test product in the test environment 03/20/2014 (5) Implement solution in production and monitor 04/01/2014 |  |  | Ongoing | High | N/A
SAMPLE

## Data Sheet (hidden)
Weakness Status | Risk Level | No weaknesses identified | Fiscal Year | Control | MARS-E Version
Ongoing | High | All weaknesses eliminated | 2014 | Other | MARS-E V. 1.0
Completed | Moderate | No review conducted | 2015 | AC | MARS-E V. 2.0
Delayed | Low | No weaknesses found | 2016 | AT
|  | System in development | 2017 | AU
|  | System reclassified – not a system | 2018 | CA
|  | System retired | 2019 | CM
CP
IA
IR
MA
MP
PE
PL
PS
RA
SA
SC
SI
PM
Privacy - AP
Privacy - AR
Privacy - DI
Privacy - DM
Privacy - IP
Privacy - SE
Privacy - TR
Privacy - UL

## Change Log (hidden)
Record of Changes
Number | Date | Reference | A = Add M = Modify D = Delete | Description of Change | Change Request #
2 | 2014-03-13 |  | M | Intial Version of the MARS-E Version 2.0 POA&M Template. Based on the POA&M Template provided to the states in 2013. Modified the original version to include the following: (1) Added a "POA&M Metrics" tab that will calculate various metrics. (2) Added dropdown lists in the "POA&M Template" tab for Weakness Status, Risk Level, Weakness Severity and If no Weakness Identified. (3) Added a new "POA&M Instructions" tab with more detailed information and guidance. (4) Added a new "POA&M Sample" tab that contains entries with the proper inputs. | N/A
2.1 | 2014-05-01 |  | M | (1) Standardized color scheme throughout the template. (2) Updated/added new header fields on all tabs. (3) Began incorporating state recommendations to include POA&M. Metrics by Control Family on the "POA&M Metrics" tab. | N/A
3 | 2014-05-19 |  | M | (1) Finalized incorporating state recommendations. (2) Began protecting all tabs so only information that is required to be entered by the states can be altered on all tabs. (3) Utilized "auto fill" on fields that contained redundant information. (4) Added a Security Control Family field on the "POA&M Template" tab. (5) Removed the Weakness Severity column on the "POA&M Template" tab. (6) Replaced the Exception or Waiver column with the Compensating Controls column. (7) Updated the "POA&M Instructions" tab and the "POA&M Sample" tab to capture all changes from the "POA&M Template" tab. | N/A
3.1 | 2014-05-28 |  | M | Incorporated recommendations from CMS and MITRE to include: (1) Removed IRS FTI Control and Privacy Control from the the dropdown list for Security Control Family on the "POA&M Template" tab. (2) Added Risk Level definitions and reference to NIST 800-30 Appendices G, H, and I on the "POA&M Instructions" tab on Instruction# 24. (3) Added additional Milestone guidance and samples on the "POA&M Instructions" tab on Instructions# 20 and 21. | N/A
3.2 | 2014-05-28 |  | M | (1) Added "Change Log" tab (2) Corrections to Version 3.1 to include: a. changed the word "chose" to "choose" on the "POA&M Instructions" tab on Instruction# 24. b. Changed the word "Moderate" to "Low" on the "POA&M Instructions" tab on Instruction# 24 under the definition of Low Risk Level. | N/A
3.3 | 2014-06-03 |  | M | Corrections to Version 3.2 (1) allow users to format rows in "POA&M Template" tab (needed to resize fields with large amounts of text). (2) allow users to format columns in "POA&M Template" tab (needed to resize fields with large amounts of text). (3) allow users to use Autofilter in "POA&M Template" tab (this allows the user to filter the rows). (4) allow users to sort in "POA&M Template" tab. (5) set print parameters for the "POA&M Metrics" tab to print all on one sheet. (6) made minor formatting updates to the "POA&M Template" tab such as field justification, font, and date format. | N/A
4 | 2015-10-08 |  | A, M & D | Updates for MARS-E Version 2.0 (1) Removed Security Control Class metrics from "POA&M Metrics" tab. (2) Added Privacy Controls Table on "POA&M Metrics" tab showing open, ongoing, delayed and completed. (3) Added two additional metrics table on "POA&M Metrics" tab; one for just Security Control metrics and one for just Privacy Control metrics. (4) Modified the Security Control Family field drop-down selection on the "POA&M Template" tab to include the newly added Privacy Controls in MARS-E Version 2.0. (5) Added a new tab titled "Risk Calculation Instructions" to assist in finding risk determination. (6) Modified #13 of the POA&M instructions on the "POA&M Instructions" tab. (7) Changed all references to State-Based Administering Entity to Administering Entity on all tabs. (8) Modified the format of all input cells on the "POA&M Template" tab. This includes input position, wrap text and row height. (9) Corrected inconsistent formatting on the "POA&M Template" tab (fonts). (10) Modified #17 (POC) of the POA&M instructions on the "POA&M Instructions" tab. | N/A
4.1 | 2016-02-03 |  | A | Updates to accommodate for the MARS-E Version 2.0 Gap Analysis (1) Added column and dropdown list in the "POA&M Template" tab for MARS-E Version. (2) Modified #25, 26, and 27 of the POA&M instructions on the "POA&M Instructions" tab to account for the addition of the MARS-E Version column and dropdown list on the "POA&M Template" tab. (3) Modified the POA&M reference visual on the "POA&M Instructions" tab to include the new MARS-E Version column. (4) Added the MARS-E Version dropdown list information on the "Data Sheet' tab. (5) Add MARS-E Version table on "POA&M Metrics" tab showing open, ongoing, delayed and completed by MARS-E Version. | N/A
4.2 | 2016-02-17 |  | M | Based on comments from MITRE, removed the word "security" from any reference to Secruity Controls on the "POA&M Template" tab, the "POA&M Instructions" tab and "POA&M Sample" tab as MARS-E 2.0 now also incorporates Privacy Controls